## Sheet1
Category | Item | Supplier | Catalogue Number | Supply Qty (per pack) | Required Qty / Batch | Units | No. Packs Required | Supplier Approval status | Tech Spec Status | Tech Spec Number | GIC Number | DCC Number | Changes Required? | Ordered? Y/N | Est. Lead Time | Received? Y/N | Lot Number | BSE/TSE Cert. | Storage Location | Cost per unit | Total cost per order | Comments | Total cost per order | Quantity available for Eng Bx
| Disposable, Sterile Powder Funnels | Avantor / VWR | 231-0650 | Pack of 24 | 7 | pack | 1 | With QA | Approved | CPI-QD-09223 | GIC-00259 | DCC-000846 | Pack and unit size + release requirements (certificate check?) |  |  |  |  | Saved in TS Folder |  | 734 | 734
ph/Cond | Conductivity Standard Solution Sachets 84 us/cm | Cole-Parmer | WZ-35653-08 | Pack of 20 | 20 | pack | 1 | Approved | Approved | CPI-QD-09761 | GIC-00281 | DCC-000916 | N/A | [6 empty] | 52 | 52 | ordered
Syringes | 10mL Syringe v1 | Fisher Scientific | 15544835 | 100 | 22 | each | 1 | Approved | Approved | CPI-QD-09019 | GIC-00253 | DCC-000841 | Sampling req + release req |  |  |  |  | Saved in TS Folder |  | 113 | 113
| 5mL Syringe v1 | Fisher Scientific | 11364881 | 125 | 12 | each | 1 | Approved | Approved | CPI-QD-09016 | GIC-00252 | DCC-000841 | Sampling req + release req |  |  |  |  | Saved in TS Folder |  | 191 | 191
| 20mL Syringe v1 | Fisher Scientific | 10569215 | 120 | 22 | each | 1 | Approved | Approved | CPI-QD-09021 | GIC-00254 | DCC-000841 | release req |  |  |  |  | Saved in TS Folder |  | 259 | 259
Tips | 1mL Pipette Tips v2 | Fisher Scientific | 16442265 | 10 | 7 | box | 2 | Approved | Approved | CPI-QD-08231 | GIC-00194 | DCC-000841 | Sampling req |  |  |  |  | Saved in TS Folder |  | 185 | 370 | Promo code for discount: 22546
| 200uL Pipette Tips v2 | Fisher Scientific | 16422265 | 10 | 7 | box | 2 | Approved | Approved | CPI-QD-08228 | GIC-00199 | DCC-000841 | Sampling req |  |  |  |  | Saved in TS Folder |  | 172 | 344 | Promo code for discount: 22546
| 5mL Pipette Tips v2 | Fisher Scientific | 16462265 | 5 | 4 | box | 3 | Approved | Approved | CPI-QD-08229 | GIC-00200 | DCC-000841 | Sampling req |  |  |  |  | Saved in TS Folder |  | 93 | 279 | Promo code for discount: 22546
| 10mL Pipette Tips (Sterile) | Fisher Scientific | 10029212 | 100 |  | each | 1 | Approved | Approved | CPI-QD-10399 | GIC-00279 | DCC-000900 | N/A | [6 empty] | 77 | 77 | Promo code for discount: 22546
| Individual tube rack (50mL) | Fisher Scientific | 11717285 | 1 | 1 | each | 6 | Approved | Draft | CPI-QD-10840 | GIC-00283 | [8 empty] | 26 | 157
| Disposable Sampling Spatulas | Fisher Scientific | 15346327 | Pack of 10 | 30 | each | 8 | Approved | Approved | CPI-QD-09391 | GIC-00266 | DCC-000841 | N/A |  |  |  |  | Saved in TS Folder |  | 33 | 260
| Disposable Spoon Spatulas | Fisher Scientific | 15614114 | 100 | 11 | each | 1 | Approved | Approved | CPI-QD-09393 | GIC-00267 | DCC-000841 | N/A |  |  |  |  | Saved in TS Folder |  | 99 | 99
| 25mL Reagent Reservoir v1 | Fisher Scientific | 16374852 | 100 | 29 | each | 1 | Approved | Approved | CPI-QD-08267 | GIC-00231 | DCC-000841 | CC - Criticality + sampling + release req + sup sig |  |  |  |  | Saved in TS Folder |  | 102 | 102
| 50mL Reagent Reservoir | Fisher Scientific | 16314862 | 100 | 29 | each | 1 | Approved | Approved | CPI-QD-09306 | GIC-00264 | DCC-000785 | N/A |  |  |  |  | Saved in TS Folder |  | 275 | 275
| 500mL Wash Bottles | Fisher Scientific | 15367047 | Pack of 5 | 12 | pack | 4 | Approved | Approved | CPI-QD-09251 | GIC-00262 | DCC-000785 | N/A |  |  |  |  | To be Obtained |  | 45 | 180
| 4L Nalgene Wide-mouth Bottle v1 | Fisher Scientific | 11369654 | 6 | 4 | each | 3 | Approved | Approved | CPI-QD-08187 | GIC-00226 | DCC-000833 | criticality, supplier name, sampling, release, supplier sign |  |  |  |  | Saved in TS Folder |  | 170 | 510 | Promo code for discount: 21983
| KimTech Wipes | Fisher Scientific | 11797968 |  | 1 | pack | 2 | Approved | Approved | CPI-QD-08243 | GIC-00234 | [6 empty] | Saved in TS Folder |  | 177 | 354 | Promo code for discount: 21673
| pH Buffer Sachet 4.01 | Mettler Toledo | 12693516 | pack of 30 | 30 | pack | 1 | Approved | Approved | CPI-QD-07541 | GIC-00178 | DCC-000916 | N/A | [6 empty] | 72 | 72
| pH Buffer Sachet 7.00 | Mettler Toledo | 12693516 | pack of 30 | 30 | Pack | 1 | Approved | Approved | CPI-QD-07542 | GIC-00179 | DCC-000916 | N/A | [6 empty] | 72 | 72
| pH Buffer Sachet 9.21 | Mettler Toledo | 12137800 | pack of 30 | 30 | Pack | 1 | Approved | Approved | CPI-QD-10476 | GIC-00282 | DCC-000916 | N/A | [6 empty] | 72 | 72
| Float-a-lyzer v1 | Sigma Aldrich | Z727253-12EA | 12 | 1 | each | 1 | Approved | Approved | CPI-QD-08224 | GIC-00198 | DCC-000833 | criticality, sampling, testing, sterility req, supplier sign |  |  |  |  | Saved in TS Folder |  | 187 | 187
| 0.1M NaOH | Sigma Aldrich | 1370589025 | 25 | 100 | L | 10 | Approved | Approved | CPI-QD-09948 | GIC-00272 | DCC-000900 | [5 empty] | Saved in TS Folder |  | 188 | 1880
| 0.5M NaOH | Sigma Aldrich | 1370609025 | 25 | 25 | L | 4 | Approved | Approved | CPI-QD-09949 | GIC-00273 | DCC-000900 | [5 empty] | Saved in TS Folder |  | 231 | 924
| Weight Boat v1 | VWR | 611-4672 | 200 | 21 | each | 1 | With QA | Approved | CPI-QD-08232 | GIC-00195 | DCC-000846 | CC - criticality + sampling + check testing + supplier sig |  |  |  |  | Saved in TS Folder |  | 87 | 87
| Scoop 30mL | VWR | 231-0382 | 100 | 11 | each | 1 | With QA | Approved | CPI-QD-08235 | GIC-00221 | DCC-000846 | Sampling req + TSE/BSE + Supplier sig |  |  |  |  | Saved in TS Folder |  | 235 | 235
| Masterflex LS Precision Pump Tubing Size 17 | VWR | MFLX96410-17 | 25ft | 2 | pack | 10 | With QA | Approved | CPI-QD-08251 | GIC-00227 | DCC-000727 | criticality, sampling, testing, sterility req, shelf-life, pack and unit size, default lot status, release, supplier sign |  |  |  |  | Saved in TS Folder |  | 128 | 1280
| Masterflex LS Precision Pump Tubing Size 16 | VWR | MFLX96410-16 | 25ft | 2 | pack | 10 | With QA | Approved | CPI-QD-08249 | GIC-00232 | DCC-000727 | criticality, sampling, shelf-life, pack and unit size, default lot status, release, supplier sign |  |  |  |  | Saved in TS Folder |  | 92 | 918
| Transfer Tubing, C-Flex®, Clear, 3/8" ID x 5/8" OD; 25 Ft, 3.2mm Wall | VWR | MFLX06422-16 | 25ft | 1 | pack | 5 | With QA | Approved | CPI-QD-09560 | GIC-00270 | DCC-000900 | [5 empty] | Saved in TS Folder |  | 148 | 740
| Transfer Tubing 1/4" ID x 7/16" OD Size 11 | VWR | MFLX06422-11 | 25ft | 4 | pack | 10 | With QA | Approved | CPI-QD-09776 | GIC-00271 | DCC-000900 | [5 empty] | Saved in TS Folder |  | 99 | 986
| Transfer Tubing, C-Flex®, Clear, 5/16" ID x 1/2" OD; 25 Ft, 2.4mm Wall | VWR | MFLX06422-14 | 25ft | 1 | pack | 5 | With QA | Approved | CPI-QD-10252 | GIC-00277 | DCC-000900 | [5 empty] | Saved in TS Folder |  | 114 | 570

## Avantor
Item | Supplier | Catalogue Number | Supply Qty (per pack) | Required Qty / Batch | Units | No. Packs Required | Supplier Approval status | Tech Spec Status | Tech Spec Number | GIC Number | DCC Number | Changes Required? | Ordered? Y/N | Est. Lead Time | Received? Y/N | Lot Number | BSE/TSE Cert. | Storage Location | Cost per unit | Total cost per order | Comments | Total cost per order | Quantity available for Eng Bx
Disposable, Sterile Powder Funnels | Avantor / VWR | 231-0650 | Pack of 24 | 7 | pack | 1 | With QA | Approved | CPI-QD-09223 | GIC-00259 | DCC-000846 | Pack and unit size + release requirements (certificate check?) |  |  |  |  | Saved in TS Folder |  | 734 | 734

## ColeParmer
Category | Item | Supplier | Catalogue Number | Supply Qty (per pack) | Required Qty / Batch | Units | No. Packs Required | Supplier Approval status | Tech Spec Status | Tech Spec Number | GIC Number | DCC Number | Changes Required? | Ordered? Y/N | Est. Lead Time | Received? Y/N | Lot Number | BSE/TSE Cert. | Storage Location | Cost per unit | Total cost per order | Comments | Total cost per order | Quantity available for Eng Bx
ph/Cond | Conductivity Standard Solution Sachets 84 us/cm | Cole-Parmer | WZ-35653-08 | Pack of 20 | 20 | pack | 1 | Approved | Approved | CPI-QD-09761 | GIC-00281 | DCC-000916 | N/A | [6 empty] | 52 | 52 | ordered

## Fisher_Scientific
Category | Item | Supplier | Catalogue Number | Supply Qty (per pack) | Required Qty / Batch | Units | No. Packs Required | Supplier Approval status | Tech Spec Status | Tech Spec Number | GIC Number | DCC Number | Changes Required? | Ordered? Y/N | Est. Lead Time | Received? Y/N | Lot Number | BSE/TSE Cert. | Storage Location | Cost per unit | Total cost per order | Comments | Total cost per order | Quantity available for Eng Bx
Syringes | 10mL Syringe v1 | Fisher Scientific | 15544835 | 100 | 22 | each | 1 | Approved | Approved | CPI-QD-09019 | GIC-00253 | DCC-000841 | Sampling req + release req |  |  |  |  | Saved in TS Folder |  | 113 | 113
| 5mL Syringe v1 | Fisher Scientific | 11364881 | 125 | 12 | each | 1 | Approved | Approved | CPI-QD-09016 | GIC-00252 | DCC-000841 | Sampling req + release req |  |  |  |  | Saved in TS Folder |  | 191 | 191
| 20mL Syringe v1 | Fisher Scientific | 10569215 | 120 | 22 | each | 1 | Approved | Approved | CPI-QD-09021 | GIC-00254 | DCC-000841 | release req |  |  |  |  | Saved in TS Folder |  | 259 | 259
Tips | 1mL Pipette Tips v2 | Fisher Scientific | 16442265 | 10 | 7 | box | 2 | Approved | Approved | CPI-QD-08231 | GIC-00194 | DCC-000841 | Sampling req |  |  |  |  | Saved in TS Folder |  | 185 | 370 | Promo code for discount: 22546
| 200uL Pipette Tips v2 | Fisher Scientific | 16422265 | 10 | 7 | box | 2 | Approved | Approved | CPI-QD-08228 | GIC-00199 | DCC-000841 | Sampling req |  |  |  |  | Saved in TS Folder |  | 172 | 344 | Promo code for discount: 22546
| 5mL Pipette Tips v2 | Fisher Scientific | 16462265 | 5 | 4 | box | 3 | Approved | Approved | CPI-QD-08229 | GIC-00200 | DCC-000841 | Sampling req |  |  |  |  | Saved in TS Folder |  | 93 | 279 | Promo code for discount: 22546
| 10mL Pipette Tips (Sterile) | Fisher Scientific | 10029212 | 100 |  | each | 1 | Approved | Approved | CPI-QD-10399 | GIC-00279 | DCC-000900 | N/A | [6 empty] | 77 | 77 | Promo code for discount: 22546
| Individual tube rack (50mL) | Fisher Scientific | 11717285 | 1 | 1 | each | 6 | Approved | Draft | CPI-QD-10840 | GIC-00283 | [8 empty] | 26 | 157
| Disposable Sampling Spatulas | Fisher Scientific | 15346327 | Pack of 10 | 30 | each | 8 | Approved | Approved | CPI-QD-09391 | GIC-00266 | DCC-000841 | N/A |  |  |  |  | Saved in TS Folder |  | 33 | 260
| Disposable Spoon Spatulas | Fisher Scientific | 15614114 | 100 | 11 | each | 1 | Approved | Approved | CPI-QD-09393 | GIC-00267 | DCC-000841 | N/A |  |  |  |  | Saved in TS Folder |  | 99 | 99
| 25mL Reagent Reservoir v1 | Fisher Scientific | 16374852 | 100 | 29 | each | 1 | Approved | Approved | CPI-QD-08267 | GIC-00231 | DCC-000841 | CC - Criticality + sampling + release req + sup sig |  |  |  |  | Saved in TS Folder |  | 102 | 102
| 50mL Reagent Reservoir | Fisher Scientific | 16314862 | 100 | 29 | each | 1 | Approved | Approved | CPI-QD-09306 | GIC-00264 | DCC-000785 | N/A |  |  |  |  | Saved in TS Folder |  | 275 | 275
| 500mL Wash Bottles | Fisher Scientific | 15367047 | Pack of 5 | 12 | pack | 4 | Approved | Approved | CPI-QD-09251 | GIC-00262 | DCC-000785 | N/A |  |  |  |  | To be Obtained |  | 45 | 180
| 4L Nalgene Wide-mouth Bottle v1 | Fisher Scientific | 11369654 | 6 | 4 | each | 3 | Approved | Approved | CPI-QD-08187 | GIC-00226 | DCC-000833 | criticality, supplier name, sampling, release, supplier sign |  |  |  |  | Saved in TS Folder |  | 170 | 510 | Promo code for discount: 21983
| KimTech Wipes | Fisher Scientific | 11797968 |  | 1 | pack | 2 | Approved | Approved | CPI-QD-08243 | GIC-00234 | [6 empty] | Saved in TS Folder |  | 177 | 354 | Promo code for discount: 21673

## Mettler_Toledo
Category | Item | Supplier | Catalogue Number | Supply Qty (per pack) | Required Qty / Batch | Units | No. Packs Required | Supplier Approval status | Tech Spec Status | Tech Spec Number | GIC Number | DCC Number | Changes Required? | Ordered? Y/N | Est. Lead Time | Received? Y/N | Lot Number | BSE/TSE Cert. | Storage Location | Cost per unit | Total cost per order | Comments | Total cost per order | Quantity available for Eng Bx
| pH Buffer Sachet 4.01 | Mettler Toledo | 12693516 | pack of 30 | 30 | pack | 1 | Approved | Approved | CPI-QD-07541 | GIC-00178 | DCC-000916 | N/A | [6 empty] | 72 | 72
| pH Buffer Sachet 7.00 | Mettler Toledo | 12693516 | pack of 30 | 30 | Pack | 1 | Approved | Approved | CPI-QD-07542 | GIC-00179 | DCC-000916 | N/A | [6 empty] | 72 | 72
| pH Buffer Sachet 9.21 | Mettler Toledo | 12137800 | pack of 30 | 30 | Pack | 1 | Approved | Approved | CPI-QD-10476 | GIC-00282 | DCC-000916 | N/A | [6 empty] | 72 | 72

## Sigma
Category | Item | Supplier | Catalogue Number | Supply Qty (per pack) | Required Qty / Batch | Units | No. Packs Required | Supplier Approval status | Tech Spec Status | Tech Spec Number | GIC Number | DCC Number | Changes Required? | Ordered? Y/N | Est. Lead Time | Received? Y/N | Lot Number | BSE/TSE Cert. | Storage Location | Cost per unit | Total cost per order | Comments | Total cost per order | Quantity available for Eng Bx
| Float-a-lyzer v1 | Sigma Aldrich | Z727253-12EA | 12 | 1 | each | 1 | Approved | Approved | CPI-QD-08224 | GIC-00198 | DCC-000833 | criticality, sampling, testing, sterility req, supplier sign |  |  |  |  | Saved in TS Folder |  | 187 | 187
| 0.1M NaOH | Sigma Aldrich | 1370589025 | 25 | 100 | L | 10 | Approved | Approved | CPI-QD-09948 | GIC-00272 | DCC-000900 | [5 empty] | Saved in TS Folder |  | 188 | 1880
| 0.5M NaOH | Sigma Aldrich | 1370609025 | 25 | 25 | L | 4 | Approved | Approved | CPI-QD-09949 | GIC-00273 | DCC-000900 | [5 empty] | Saved in TS Folder |  | 231 | 924

## VWR
Category | Item | Supplier | Catalogue Number | Supply Qty (per pack) | Required Qty / Batch | Units | No. Packs Required | Supplier Approval status | Tech Spec Status | Tech Spec Number | GIC Number | DCC Number | Changes Required? | Ordered? Y/N | Est. Lead Time | Received? Y/N | Lot Number | BSE/TSE Cert. | Storage Location | Cost per unit | Total cost per order | Comments | Total cost per order | Quantity available for Eng Bx
| Weight Boat v1 | VWR | 611-4672 | 200 | 21 | each | 1 | With QA | Approved | CPI-QD-08232 | GIC-00195 | DCC-000846 | CC - criticality + sampling + check testing + supplier sig |  |  |  |  | Saved in TS Folder |  | 87 | 87
| Scoop 30mL | VWR | 231-0382 | 100 | 11 | each | 1 | With QA | Approved | CPI-QD-08235 | GIC-00221 | DCC-000846 | Sampling req + TSE/BSE + Supplier sig |  |  |  |  | Saved in TS Folder |  | 235 | 235
| Masterflex LS Precision Pump Tubing Size 17 | VWR | MFLX96410-17 | 25ft | 2 | pack | 10 | With QA | Approved | CPI-QD-08251 | GIC-00227 | DCC-000727 | criticality, sampling, testing, sterility req, shelf-life, pack and unit size, default lot status, release, supplier sign |  |  |  |  | Saved in TS Folder |  | 128 | 1280
| Masterflex LS Precision Pump Tubing Size 16 | VWR | MFLX96410-16 | 25ft | 2 | pack | 10 | With QA | Approved | CPI-QD-08249 | GIC-00232 | DCC-000727 | criticality, sampling, shelf-life, pack and unit size, default lot status, release, supplier sign |  |  |  |  | Saved in TS Folder |  | 92 | 918
| Transfer Tubing, C-Flex®, Clear, 3/8" ID x 5/8" OD; 25 Ft, 3.2mm Wall | VWR | MFLX06422-16 | 25ft | 1 | pack | 5 | With QA | Approved | CPI-QD-09560 | GIC-00270 | DCC-000900 | [5 empty] | Saved in TS Folder |  | 148 | 740
| Transfer Tubing 1/4" ID x 7/16" OD Size 11 | VWR | MFLX06422-11 | 25ft | 4 | pack | 10 | With QA | Approved | CPI-QD-09776 | GIC-00271 | DCC-000900 | [5 empty] | Saved in TS Folder |  | 99 | 986
| Transfer Tubing, C-Flex®, Clear, 5/16" ID x 1/2" OD; 25 Ft, 2.4mm Wall | VWR | MFLX06422-14 | 25ft | 1 | pack | 5 | With QA | Approved | CPI-QD-10252 | GIC-00277 | DCC-000900 | [5 empty] | Saved in TS Folder |  | 114 | 570