## Total
Raw Materials | Manufacturer | Manufacturer Reference No. | Supplier | Cat. No. | Quality | Supply Qty | Required Qty (per Batch) | Units | No. Required | Supplier Approval Status | Tech Spec Status | Tech Spec Number | GIx Number | On Procurement Plan? Y/N | Est. Lead time | Received? Y/N | Lot Number | TSE/BSE | Cost per unit | Total cost per order
DMPE-PEG2000 | Avanti | 730150 | Avanti | 730150 | GMP Grade | 10g | 250 | mg | 2 | With QA | Approved | CPI-QD-10011 | GIR-00022 | N |  | N |  | Saved in TS Folder | 5662.5 | 11325
DSPC | Avanti | 730365 | Avanti | 730365 | GMP Grade | 10g | 400 | mg | 2 | With QA | Approved | CPI-QD-10003 | GIR-00021 | N |  | N |  | Saved in TS Folder | 1404.6 | 2809.2
ATP, 100mM | New England Biolabs | G1000B | New England Biolabs | G1000B | GMP Grade | 1mL | 1 | mL | 3 - from the same Lot | Approved | Approved | CPI-QD-09856 | GIR-00004 | N | 2-3 weeks | N |  | Saved in TS Folder | 192 | 576
CTP, 100mM | New England Biolabs | G1003B | New England Biolabs | G1003B | GMP Grade | 1mL | 1 | mL | 3 - from the same Lot | Approved | Approved | CPI-QD-09858 | GIR-00006 | N | 2-3 weeks | N |  | Saved in TS Folder | 192 | 576
GTP, 100mM | New England Biolabs | G1001B | New England Biolabs | G1001B | GMP Grade | 1mL | 1 | mL | 3 - from the same Lot | Approved | Approved | CPI-QD-09857 | GIR-00005 | N | 2-3 weeks | N |  | Saved in TS Folder | 192 | 576
UTP, 100mM | New England Biolabs | G1002B | New England Biolabs | G1002B | GMP Grade | 1mL | 1 | mL | 3 - from the same Lot | Approved | Approved | CPI-QD-09973 | GIR-00007 | N | 2-3 weeks | N |  | Saved in TS Folder | 192 | 576
Synthecol Synthetic Cholesterol Emprove Expert | Sigma Aldrich | 1046720001 | Sigma Aldrich | 1046720001 | GMP Grade | 1g | 500 | mg | 3 - from the same Lot | Approved | Approved | CPI-QD-09910 | GIR-00024 | N | 10-15 days | N |  | Saved in TS Folder | £65 | £65
1M Hydrochloric Acid, Emprove Expert | Sigma Aldrich | 1101652500 | Sigma Aldrich | 1101652500 | GMP Grade | 2.5L | 2.5 | L | 2 | Approved | Approved | CPI-QD-09911 | GIR-00015 | N | 10-15 days | N |  | Saved in TS Folder | £53 | £477
Dulbecco's Phosphate Buffered Saline 10X | Sigma Aldrich | 59331C-1000ML | Sigma Aldrich | 59331C-1000ML | Further Manufacturing Use | 1L | 4 | L | 9 - from the same Lot | Approved | Approved | CPI-QD-09913 | GIR-00025 | N | 180 days | N |  | Saved in TS Folder
Magnesium Acetate Tetrahydrate, EMSURE ACS, Reag. Ph. Eur | Sigma Aldrich | 1058190250 | Sigma Aldrich | 1058190250 | Ph. Eur Grade | 250g | 2.15 | g | 2 | Approved | Approved | CPI-QD-09908 | GIR-00018 | N | Available 4 Jun; 10-15 days | N |  | Saved in TS Folder | £69 | £138
Sodium acetate anhydrous Emprove Expert ChP USO | Sigma Aldrich | 1282021001 | Sigma Aldrich | 1282021001 | GMP Grade | 1kg | 40.12 | g | 2 | Approved | Approved | CPI-QD-09906 | GIR-00012 | N | 10-15 days | N |  | Saved in TS Folder | £53 | £106
Sodium Chloride Emprove Expert Ph. Eur., BP, JP, USP | Sigma Aldrich | 1162241000 | Sigma Aldrich | 1162241000 | GMP Grade | 1kg | 45.66 | g | 2 | Approved | Approved | CPI-QD-09907 | GIR-00013 | N | 10-15 days | N |  | Saved in TS Folder | £296 | £2664
Sucrose Emprove Expert, Ph. Eur., ChP, JP, NF | Sigma Aldrich | 1037891000 | Sigma Aldrich | 1037891000 | GMP Grade | 1kg | 3.6 | kg | 9 - from the same Lot | Approved | Approved | CPI-QD-09909 | GIR-00023 | N | 10-15 days | N |  | Saved in TS Folder | 402 | 1206
Ethanol Ph. Eur. | VWR | 20816.298DP | VWR | 20816.298DP | Ph. Eur Grade | 1L | 285 | g | 9 - from the same Lot | With QA | Approved | CPI-QD-09932 | GIR-00014 | N | immediate | N |  | Saved in TS Folder | £111.75 | £1264.41
Lithium chloride ≥99.0%, AnalaR NORMAPUR® Reag. Ph. Eur. | VWR | 25012.237 | VWR | 25012.237 | Ph. Eur Grade | 250g | 12.72 | g | 2 | With QA | Approved | CPI-QD-09915 | GIR-00017 | N | 7-10 days | N |  | Saved in TS Folder | £69.52 | £139.04
Note on M2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Waiting on vendor info on "custom" CoA
Note on M3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Waiting on vendor info for "custom" CoAs
Note on C10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 55120C-20BC originally ordered but cancelled for lead times
Note on U15: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1,005.75 + Alcohol Tax 258.66

## Avanti_cold
Raw Materials | Manufacturer | Manufacturer Reference No. | Supplier | Cat. No. | Quality | Supply Qty | Required Qty (per Batch) | Units | No. Required | Supplier Approval Status | Tech Spec Status | Tech Spec Number | GIx Number | On Procurement Plan? Y/N | Est. Lead time | Received? Y/N | Lot Number | TSE/BSE | Cost per unit | Total cost per order
DMPE-PEG2000 | Avanti | 730150 | Avanti | 730150 | GMP Grade | 10g | 250 | mg | 2 | With QA | Approved | CPI-QD-10011 | GIR-00022 | N |  | N |  | Saved in TS Folder | 5662.5 | 11325
DSPC | Avanti | 730365 | Avanti | 730365 | GMP Grade | 10g | 400 | mg | 2 | With QA | Approved | CPI-QD-10003 | GIR-00021 | N |  | N |  | Saved in TS Folder | 1404.6 | 2809.2
Note on M2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Waiting on vendor info on "custom" CoA
Note on M3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Waiting on vendor info for "custom" CoAs

## NEB_cold
Raw Materials | Manufacturer | Manufacturer Reference No. | Supplier | Cat. No. | Quality | Supply Qty | Required Qty (per Batch) | Units | No. Required | Supplier Approval Status | Tech Spec Status | Tech Spec Number | GIx Number | On Procurement Plan? Y/N | Est. Lead time | Received? Y/N | Lot Number | TSE/BSE | Cost per unit | Total cost per order
ATP, 100mM | New England Biolabs | G1000B | New England Biolabs | G1000B | GMP Grade | 1mL | 1 | mL | 3 - from the same Lot | Approved | Approved | CPI-QD-09856 | GIR-00004 | N | 2-3 weeks | N |  | Saved in TS Folder | 192 | 576
CTP, 100mM | New England Biolabs | G1003B | New England Biolabs | G1003B | GMP Grade | 1mL | 1 | mL | 3 - from the same Lot | Approved | Approved | CPI-QD-09858 | GIR-00006 | N | 2-3 weeks | N |  | Saved in TS Folder | 192 | 576
GTP, 100mM | New England Biolabs | G1001B | New England Biolabs | G1001B | GMP Grade | 1mL | 1 | mL | 3 - from the same Lot | Approved | Approved | CPI-QD-09857 | GIR-00005 | N | 2-3 weeks | N |  | Saved in TS Folder | 192 | 576
UTP, 100mM | New England Biolabs | G1002B | New England Biolabs | G1002B | GMP Grade | 1mL | 1 | mL | 3 - from the same Lot | Approved | Approved | CPI-QD-09973 | GIR-00007 | N | 2-3 weeks | N |  | Saved in TS Folder | 192 | 576

## Sigma_cold
Raw Materials | Manufacturer | Manufacturer Reference No. | Supplier | Cat. No. | Quality | Supply Qty | Required Qty (per Batch) | Units | No. Required | Supplier Approval Status | Tech Spec Status | Tech Spec Number | GIx Number | On Procurement Plan? Y/N | Est. Lead time | Received? Y/N | Lot Number | TSE/BSE | Cost per unit | Total cost per order
Synthecol Synthetic Cholesterol Emprove Expert | Sigma Aldrich | 1046720001 | Sigma Aldrich | 1046720001 | GMP Grade | 1g | 500 | mg | 3 - from the same Lot | Approved | Approved | CPI-QD-09910 | GIR-00024 | N | 10-15 days | N |  | Saved in TS Folder | 402 | 1206

## Sigma_lot
Raw Materials | Manufacturer | Manufacturer Reference No. | Supplier | Cat. No. | Quality | Supply Qty | Required Qty (per Batch) | Units | No. Required | Supplier Approval Status | Tech Spec Status | Tech Spec Number | GIx Number | On Procurement Plan? Y/N | Est. Lead time | Received? Y/N | Lot Number | TSE/BSE | Cost per unit | Total cost per order
Dulbecco's Phosphate Buffered Saline 10X | Sigma Aldrich | 59331C-1000ML | Sigma Aldrich | 59331C-1000ML | Further Manufacturing Use | 1L | 4 | L | 9 - from the same Lot | Approved | Approved | CPI-QD-09913 | GIR-00025 | N | 180 days | N |  | Saved in TS Folder | £53 | £477
Sucrose Emprove Expert, Ph. Eur., ChP, JP, NF | Sigma Aldrich | 1037891000 | Sigma Aldrich | 1037891000 | GMP Grade | 1kg | 3.6 | kg | 9 - from the same Lot | Approved | Approved | CPI-QD-09909 | GIR-00023 | N | 10-15 days | N |  | Saved in TS Folder | £296 | £2664
3141
Note on C2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 55120C-20BC originally ordered but cancelled for lead times

## VWR_lot
Raw Materials | Manufacturer | Manufacturer Reference No. | Supplier | Cat. No. | Quality | Supply Qty | Required Qty (per Batch) | Units | No. Required | Supplier Approval Status | Tech Spec Status | Tech Spec Number | GIx Number | On Procurement Plan? Y/N | Est. Lead time | Received? Y/N | Lot Number | TSE/BSE | Cost per unit | Total cost per order
Ethanol Ph. Eur. | VWR | 20816.298DP | VWR | 20816.298DP | Ph. Eur Grade | 1L | 285 | g | 9 - from the same Lot | With QA | Approved | CPI-QD-09932 | GIR-00014 | N | immediate | N |  | Saved in TS Folder | £111.75 | 1264.41
Note on U2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1,005.75 + Alcohol Tax 258.66

## Sigma
Raw Materials | Manufacturer | Manufacturer Reference No. | Supplier | Cat. No. | Quality | Supply Qty | Required Qty (per Batch) | Units | No. Required | Supplier Approval Status | Tech Spec Status | Tech Spec Number | GIx Number | On Procurement Plan? Y/N | Est. Lead time | Received? Y/N | Lot Number | TSE/BSE | Cost per unit | Total cost per order
1M Hydrochloric Acid, Emprove Expert | Sigma Aldrich | 1101652500 | Sigma Aldrich | 1101652500 | GMP Grade | 2.5L | 2.5 | L | 2 | Approved | Approved | CPI-QD-09911 | GIR-00015 | N | 10-15 days | N |  | Saved in TS Folder | £65 | 130
Magnesium Acetate Tetrahydrate, EMSURE ACS, Reag. Ph. Eur | Sigma Aldrich | 1058190250 | Sigma Aldrich | 1058190250 | Ph. Eur Grade | 250g | 2.15 | g | 2 | Approved | Approved | CPI-QD-09908 | GIR-00018 | N | Available 4 Jun; 10-15 days | N |  | Saved in TS Folder | 113 | 226
Sodium acetate anhydrous Emprove Expert ChP USO | Sigma Aldrich | 1282021001 | Sigma Aldrich | 1282021001 | GMP Grade | 1kg | 40.12 | g | 2 | Approved | Approved | CPI-QD-09906 | GIR-00012 | N | 10-15 days | N |  | Saved in TS Folder | £69 | £138
Sodium Chloride Emprove Expert Ph. Eur., BP, JP, USP | Sigma Aldrich | 1162241000 | Sigma Aldrich | 1162241000 | GMP Grade | 1kg | 45.66 | g | 2 | Approved | Approved | CPI-QD-09907 | GIR-00013 | N | 10-15 days | N |  | Saved in TS Folder | £53 | 106
600

## VWR
Raw Materials | Manufacturer | Manufacturer Reference No. | Supplier | Cat. No. | Quality | Supply Qty | Required Qty (per Batch) | Units | No. Required | Supplier Approval Status | Tech Spec Status | Tech Spec Number | GIx Number | On Procurement Plan? Y/N | Est. Lead time | Received? Y/N | Lot Number | TSE/BSE | Cost per unit | Total cost per order
Lithium chloride ≥99.0%, AnalaR NORMAPUR® Reag. Ph. Eur. | VWR | 25012.237 | VWR | 25012.237 | Ph. Eur Grade | 250g | 12.72 | g | 2 | With QA | Approved | CPI-QD-09915 | GIR-00017 | N | 7-10 days | N |  | Saved in TS Folder | £69.52 | £139.04